## Vi-checklist
Mã công việc | Loại | Người phụ trách | Phụ thuộc | Công việc | Phạm vi riêng | Tiêu chí hoàn thành | Trạng thái | Liên kết / minh chứng | Mã phản hồi gốc
T01 | Lập trình | Thành viên 1 | Không | Xác minh nhãn đích, tập dữ liệu và quy trình đánh giá | Nhãn đích; ID các tập; metric, seed và định dạng dự đoán dùng chung | Ghi rõ nhãn đích của từng mô hình; kiểm tra nguồn gốc và phần giao nhau của train/dev/test; hoàn thiện một quy trình đánh giá dùng chung. Thống nhất định nghĩa nhãn với T09 trước khi chốt cấu hình. | Chưa bắt đầu |  | R3-01; R3-02; R3-03; R2-05; R4-01
T02 | Lập trình | Thành viên 1 | T01 | Chạy các baseline có thể so sánh và lặp nhiều seed | Baseline văn bản, hình ảnh, multimodal trên nhãn MM; các cấu hình s1-s4 giữ lại | Chạy các mô hình có yếu tố ngẫu nhiên với seed đã công bố; lưu dự đoán theo từng mẫu; kiểm tra dữ liệu vào, cache, checkpoint và đầu ra để giải thích điểm số trùng nhau. | Chưa bắt đầu |  | R2-05; R3-02; R3-04; R4-01; R5-01
T03 | Lập trình | Thành viên 1 | T02; T05; T06 | Tổng hợp độ bất định và kiểm tra số liệu kết quả | Toàn bộ kết quả benchmark, OCR và đánh giá chéo nền tảng | Báo cáo trung bình, độ lệch chuẩn và khoảng tin cậy phù hợp; chỉ kiểm định theo cặp khi hợp lý. Đối chiếu mọi số liệu trong bảng và hình với kết quả đã lưu. | Chưa bắt đầu |  | R2-05; R3-04; R4-01; R4-03; R5-01
T04 | Viết nội dung | Thành viên 1 | T03 | Viết lại quy trình thí nghiệm và kết quả chính | Mục IV.A-F và Bảng VII | Nêu thiết kế cùng nhãn đích, cách chia tập, seed, cách chọn mô hình và phương pháp ước lượng độ bất định. Chỉ so sánh kết quả tương ứng; giải thích điểm số lặp lại và không phóng đại lợi ích multimodal. | Chưa bắt đầu |  | R3-02; R2-05; R3-04; R2-08; R4-03; R5-01
T05 | Lập trình | Nhật Vũ | Không | Xây dựng và chạy thí nghiệm OCR | Chỉ caption, chỉ OCR, caption+OCR, ảnh+caption, ảnh+caption+OCR | Có thể chuẩn bị dữ liệu OCR ngay; thống nhất cấu hình với T01 trước khi chạy. Tái sử dụng đối chứng từ T02; báo cáo trên toàn bộ test và riêng nhóm có/không có OCR, kèm số mẫu và phân bố lớp. | Chưa bắt đầu |  | R2-04; R3-05; R4-02; R5-03
T06 | Lập trình | Nhật Vũ | Không | Đánh giá chéo giữa Facebook và Threads | Facebook sang Threads, Threads sang Facebook và đối chứng trong từng nền tảng | Có thể chuẩn bị cách chia dữ liệu ngay; thống nhất cấu hình với T01 trước khi chạy. Dùng nhãn MM và seed đã công bố; không điều chỉnh trên tập test đích; báo cáo số mẫu và phân bố lớp nguồn/đích. | Chưa bắt đầu |  | R4-01; R4-03; R5-04
T07 | Lập trình | Nhật Vũ | T02; T05; T06 | Phân tích lỗi và chọn ví dụ | Phân tích theo (T,I,MM), OCR và nền tảng | Xuất số mẫu và tỷ lệ FP/FN, đặc biệt với nhóm (0,0,1); cung cấp ID mẫu thật và dự đoán của mô hình để phân tích định tính. | Chưa bắt đầu |  | R2-04; R5-02; R5-06
T08 | Viết nội dung | Nhật Vũ | T03; T07 | Viết kết quả OCR, nền tảng và phân tích lỗi | Các mục OCR/nền tảng mới; Mục V và Hình 4 | Trình bày phương pháp, số mẫu, độ bất định và kết quả. Bổ sung 4-6 ví dụ thật đã ẩn danh, gồm lỗi (0,0,1) và một trường hợp thành công để đối chiếu; diễn giải thận trọng. | Chưa bắt đầu |  | R2-04; R3-05; R4-02; R4-03; R5-02; R5-03; R5-04; R5-06
T09 | Viết nội dung | Thành viên 3 | Không | Làm rõ định nghĩa nhãn và độ tin cậy của chú thích | Mục III.A/D và Bảng III-IV | Định nghĩa T, I, MM và quan hệ giữa các nhãn. Nêu số người chú thích, cách xử lý bất đồng, tỷ lệ sửa nhãn và tính độc lập của test. Gọi kappa hiện có là độ đồng thuận LLM-người; chỉ tính đồng thuận giữa người nếu đã có nhãn độc lập, nếu không thì nêu hạn chế. | Chưa bắt đầu |  | R2-03; R3-01; R3-03; R4-01; R4-03; R5-02
T10 | Viết nội dung | Thành viên 3 | T09 | Làm rõ hệ phân loại và cách diễn giải phân bố nhãn | Mục III.C/E; Bảng II, V-VI; Hình 2-3 | Nêu rõ có lưu nhãn của bảy kiểu mỉa mai hay không và chúng được dùng thế nào; chỉ phân tích khi dữ liệu đã có. Kiểm tra số liệu; mô tả (0,0,1) là sự phụ thuộc theo chú thích, không xem là bằng chứng mô hình đơn phương thức không phù hợp. | Chưa bắt đầu |  | R2-04; R2-08; R4-03; R5-02; R5-06
T11 | Viết nội dung | Thành viên 3 | T09 | Viết phần hạn chế | Chất lượng chú thích, hệ phân loại, thiên lệch nền tảng và phạm vi thí nghiệm | Nêu hạn chế của nhãn chủ yếu do LLM tạo, mức xác minh của con người, bằng chứng về hệ phân loại, chênh lệch nền tảng và các thí nghiệm đã hoàn thành. Bổ sung hạn chế từ T03/T06 trước khi đánh dấu hoàn thành. | Chưa bắt đầu |  | R2-03; R4-01; R4-03; R5-04; R2-08
T12 | Viết nội dung | Thư Nhi | Không | Làm rõ điểm mới và so sánh các bộ dữ liệu | Mở đầu, Nghiên cứu liên quan và Mục IV.G | So sánh SarcNet, ViMMSD và các bộ dữ liệu tiếng Anh phù hợp theo quy mô, ngôn ngữ, không gian nhãn, OCR và cách xác minh bằng nguồn đã kiểm tra. Giải thích khác biệt về metric và nhãn; không so sánh trực tiếp điểm số khi không tương thích. | Chưa bắt đầu |  | R2-02; R2-06; R4-03; R5-05
T13 | Viết nội dung | Thư Nhi | Không | Viết tuyên bố đạo đức và phát hành dữ liệu | Mục đạo đức/phát hành mới và tài liệu phát hành | Xác minh cách thu thập, quyền riêng tư và ẩn danh, xử lý ảnh chụp hội thoại, bản quyền, điều khoản nền tảng, phạm vi được phép chia sẻ, giấy phép và đầu mối gỡ dữ liệu. Giữ các điểm chưa xác minh dưới dạng thông tin còn thiếu. | Chưa bắt đầu |  | R2-07; R3-06
T14 | Viết nội dung | Thư Nhi | T04; T08; T10; T11; T12; T13 | Sửa các kết luận và tích hợp bản camera-ready | Tóm tắt, kết luận, tài liệu tham khảo, PDF cuối và đối chiếu phản hồi | Giảm các khẳng định quá mạnh về độ tin cậy và ưu thế multimodal; sửa mô tả 27,31% thuộc staged gating; gộp các phần đã duyệt; soát hình, tài liệu tham khảo và định dạng; bảo đảm mỗi yêu cầu của reviewer được xử lý hoặc nêu rõ hạn chế. | Chưa bắt đầu |  | R2-02; R2-03; R2-04; R2-05; R2-06; R2-07; R2-08; R3-01; R3-02; R3-03; R3-04; R3-05; R3-06; R4-01; R4-02; R4-03; R5-01; R5-02; R5-03; R5-04; R5-05; R5-06

## Checklist (hidden)
Task ID | Type | Owner | Depends on | Task | Exclusive scope | Done when | Status | Evidence link / note | Raw feedback IDs
T01 | Coding | Person 1 | None | Validate targets, splits, and evaluation workflow | Targets; split IDs; shared metrics, seeds, prediction format | Document each model target, verify train/dev/test provenance and overlap, and make one reusable evaluation workflow. Agree final label definitions with T09 before freezing settings. | Not started |  | R3-01; R3-02; R3-03; R2-05; R4-01
T02 | Coding | Person 1 | T01 | Run comparable baselines and repeated experiments | Selected text, image, and multimodal baselines on MM; retained s1-s4 runs | Run selected stochastic models with declared seeds, save per-sample predictions, and investigate identical scores through inputs, caches, checkpoints, and outputs. | Not started |  | R2-05; R3-02; R3-04; R4-01; R5-01
T03 | Coding | Person 1 | T02; T05; T06 | Aggregate uncertainty and verify result numbers | All final benchmark, OCR, and platform outputs | Report mean/SD and a justified confidence interval; use paired significance tests only when appropriate. Reconcile every table and figure value with saved outputs. | Not started |  | R2-05; R3-04; R4-01; R4-03; R5-01
T04 | Writing | Person 1 | T03 | Rewrite the experimental protocol and main results | Section IV.A-F and Table VII | State the shared-target design, splits, seeds, model selection, and uncertainty method. Report matched comparisons and explain repeated scores without overstating multimodal gains. | Not started |  | R3-02; R2-05; R3-04; R2-08; R4-03; R5-01
T05 | Coding | Person 2 | None | Implement and run the OCR experiment | Caption-only, OCR-only, caption+OCR, image+caption, image+caption+OCR | Prepare OCR inputs immediately; align settings with T01 before running. Reuse T02 controls and report full-test plus OCR-present/absent results with sample and class counts. | Not started |  | R2-04; R3-05; R4-02; R5-03
T06 | Coding | Person 2 | None | Run cross-platform evaluation | Facebook-to-Threads, Threads-to-Facebook, within-platform controls | Prepare platform splits immediately; align settings with T01 before running. Use the MM target, declared seeds, untouched target test data, and report source/target class counts. | Not started |  | R4-01; R4-03; R5-04
T07 | Coding | Person 2 | T02; T05; T06 | Produce error slices and candidate examples | (T,I,MM), OCR, and platform diagnostics | Export support counts and FP/FN rates, especially for (0,0,1), and provide real sample IDs and predictions for qualitative analysis. | Not started |  | R2-04; R5-02; R5-06
T08 | Writing | Person 2 | T03; T07 | Write OCR, platform, and qualitative error findings | New OCR/platform subsections; Section V and Figure 4 | Report methods, counts, uncertainty, and findings. Add 4-6 anonymized real cases, including (0,0,1) failures and one contrasting success, using cautious explanations. | Not started |  | R2-04; R3-05; R4-02; R4-03; R5-02; R5-03; R5-04; R5-06
T09 | Writing | Person 3 | None | Clarify label semantics and annotation reliability | Section III.A/D and Tables III-IV | Define T, I, and MM and their allowed relationships. Report annotator count, adjudication, correction rate, and test independence. Call existing kappa LLM-human agreement; compute human-human agreement only if independent labels already exist, otherwise state the limitation. | Not started |  | R2-03; R3-01; R3-03; R4-01; R4-03; R5-02
T10 | Writing | Person 3 | T09 | Resolve the taxonomy and label-distribution interpretation | Section III.C/E; Tables II, V-VI; Figures 2-3 | State whether seven-type labels exist and how they were used; analyze them only if data already exist. Verify counts and describe (0,0,1) as annotated dependence, not proof of unimodal inadequacy. | Not started |  | R2-04; R2-08; R4-03; R5-02; R5-06
T11 | Writing | Person 3 | T09 | Write the limitations | Annotation quality, taxonomy scope, platform bias, experimental coverage | State limits of LLM-dominated labels, available human validation, taxonomy evidence, platform prevalence, and completed experiments. Add final experimental limitations from T03/T06 before marking done. | Not started |  | R2-03; R4-01; R4-03; R5-04; R2-08
T12 | Writing | Person 4 | None | Strengthen novelty and dataset comparisons | Introduction, Related Work, and Section IV.G | Compare SarcNet, ViMMSD, and relevant English datasets by size, language, label space, OCR, and validation using verified sources. Explain metric/label-space differences and avoid direct score claims when metrics differ. | Not started |  | R2-02; R2-06; R4-03; R5-05
T13 | Writing | Person 4 | None | Write the ethics and data-release statement | New ethics/release subsection and release materials | Verify collection conditions, privacy and anonymization, screenshot handling, copyright, platform terms, permitted distribution, licenses, and removal contact. Keep unknown facts explicit. | Not started |  | R2-07; R3-06
T14 | Writing | Person 4 | T04; T08; T10; T11; T12; T13 | Revise claims and integrate the camera-ready manuscript | Abstract, conclusion, references, final PDF, reviewer coverage | Moderate reliability and superiority claims, correct the 27.31% staged-gating description, merge approved sections, proofread figures/references/formatting, and account for every reviewer request or documented limitation. | Not started |  | R2-02; R2-03; R2-04; R2-05; R2-06; R2-07; R2-08; R3-01; R3-02; R3-03; R3-04; R3-05; R3-06; R4-01; R4-02; R4-03; R5-01; R5-02; R5-03; R5-04; R5-05; R5-06

## Raw feedback
Feedback ID | Reviewer | Review field | Raw text — full wording
R2-01 | Reviewer #2 | Comments to Authors | - The paper addresses a real gap: Vietnamese multimodal sarcasm resources are scarce, and existing work is mostly binary. A 7,355-sample corpus with paired text–image inputs, auxiliary OCR, and explicit Text / Image / Multimodal labels is a useful community resource
R2-02 | Reviewer #2 | Comments to Authors | - Contribution is mostly a dataset plus oﬀ-the-shelf baselines; there is no new model, fusion method, or theoretical insight at IEEE conference level.
R2-03 | Reviewer #2 | Comments to Authors | - About 90% of labels come from LLMs, with human checks on only 10% of the data and no independent human–human IAA, so training-label quality is not established.
R2-04 | Reviewer #2 | Comments to Authors | - The seven-type sarcasm taxonomy and the collected OCR text are advertised but never used in experiments or analysis.
R2-05 | Reviewer #2 | Comments to Authors | -Results are from a single run, with no seeds, confidence intervals, or significance tests; several models even return identical scores across diﬀerent text ablations.
R2-06 | Reviewer #2 | Comments to Authors | - Related work does not quantify what is new versus SarcNet, ViMMSD, and standard English MSD datasets.
R2-07 | Reviewer #2 | Comments to Authors | -Ethics, PII, platform ToS, and a data-release license are missing, which is a serious issue for crawled Facebook/Threads posts and conversation screenshots.
R2-08 | Reviewer #2 | Comments to Authors | -The headline 68.84% F1-macro is only marginally better than strong text- Page 1 of 5 only models, so the multimodal-gain claim is overstated.
R2-SCORE | Reviewer #2 | Overall Score | Weak Reject
R3-00 | Reviewer #3 | Comments to Authors | This paper introduces ViMMSarc-Fine, a Vietnamese multimodal sarcasm dataset containing 7,355 text–image samples collected from Facebook and Threads. Its main strength is the fine-grained annotation of sarcasm at the textual, visual, and multimodal levels. The two-stage LLM–human annotation process, controlled preprocessing settings, and evaluation of multiple unimodal and multimodal baselines provide a useful starting point for Vietnamese multimodal sarcasm research. Nevertheless, several issues should be addressed in the final version:
R3-01 | Reviewer #3 | Comments to Authors | The definitions and logical relationships among the text, image, and multimodal labels should be clarified, particularly for cases where a unimodal label is positive but the multimodal label is negative.
R3-02 | Reviewer #3 | Comments to Authors | Text-only, image-only, and multimodal models appear to predict diﬀerent target labels. Their results should therefore not be directly compared as evidence that multimodal models outperform unimodal ones. Ideally, all models should also be evaluated using the same final sarcasm label.
R3-03 | Reviewer #3 | Comments to Authors | The authors should provide more details about human annotation, including the number of annotators, disagreement resolution, the proportion of LLM labels corrected by humans, and whether the test set was independently annotated.
R3-04 | Reviewer #3 | Comments to Authors | Results are reported from only one run. Multiple random seeds or confidence intervals would improve the reliability of the comparisons.
R3-05 | Reviewer #3 | Comments to Authors | Since OCR text is available for 67.18% of the samples, adding at least one OCR-enhanced baseline would strengthen the experimental evaluation.
R3-06 | Reviewer #3 | Comments to Authors | The paper should include a brief ethics and data-release statement addressing privacy, anonymization, copyright, and the handling of social- Page 2 of 5 media content.
R3-SCORE | Reviewer #3 | Overall Score | Weak Accept
R4-00 | Reviewer #4 | Comments to Authors | The paper introduces ViMMSarc-Fine, a Vietnamese multimodal sarcasm dataset with modality-level annotations for text, image, and multimodal sarcasm, together with auxiliary OCR text. The dataset construction is carefully motivated, and the two-round annotation protocol, manually verified test subset, broad baseline coverage, and error analysis are useful contributions. The observation that a substantial fraction of positive samples require joint text–image interpretation also makes the resource potentially valuable for studying cross-modal reasoning.
R4-01 | Reviewer #4 | Comments to Authors | However, several aspects currently limit the strength of the contribution. First, most labels are produced through an LLM-assisted annotation pipeline, while only 10% of the dataset is manually verified; therefore, the reported agreement should be interpreted more cautiously as LLM–human agreement rather than strong evidence of annotation reliability in the conventional inter-annotator sense. Second, the benchmark is based on single runs and does not report variance or statistical significance. Third, the strong diﬀerence in sarcasm prevalence between Facebook and Threads raises potential platform-bias concerns that are not directly evaluated through cross-platform testing.
R4-02 | Reviewer #4 | Comments to Authors | A particularly important revision would be to evaluate the contribution of the OCR signal. OCR text is available for 67.18% of the dataset, yet it is not explicitly incorporated as an independent modality in the main benchmark. An ablation comparing caption-only, OCR-only, caption+OCR, image+caption, and image+caption+OCR settings would clarify whether OCR materially improves detection, especially for screenshots and text-rich memes, and would better justify OCR as part of the dataset contribution. Page 3 of 5
R4-03 | Reviewer #4 | Comments to Authors | The manuscript should also moderate several overclaims. Statements that the annotation pipeline “validates the high reliability” of the dataset, that the label distribution “proves” unimodal approaches are fundamentally inadequate, or that the benchmark definitively establishes multimodal superiority are stronger than what the current evidence supports. The reported results instead suggest substantial multimodal dependence and promising annotation consistency, but stronger human validation, repeated runs, and cross-platform/generalization experiments would be needed to support such broader claims.
R4-SCORE | Reviewer #4 | Overall Score | Borderline
R5-00 | Reviewer #5 | Comments to Authors | The paper introduces ViMMSarc-Fine, a well-motivated Vietnamese multimodal sarcasm dataset with 7,355 samples and fine-grained text, image, and multimodal annotations. The two-round annotation procedure is carefully designed, and the reported human–LLM agreement is substantial, with Cohen’s κ of 0.7600, 0.7436, and 0.7987 for text, image, and multimodal labels, respectively. The dataset provides useful diagnostic value, particularly because 49.71% of sarcastic samples require genuine cross-modal interaction, and the paper establishes a reasonably comprehensive benchmark across text-only, image-only, and multimodal models. The experimental analysis is generally solid and includes meaningful preprocessing and emoji ablations. However, several aspects could still be improved to strengthen the paper further:
R5-01 | Reviewer #5 | Comments to Authors | (1) Report results over multiple random seeds rather than a single run to demonstrate statistical stability.
R5-02 | Reviewer #5 | Comments to Authors | (2) Provide stronger analysis of annotation disagreements and diﬃcult samples, especially for modality-level labels.
R5-03 | Reviewer #5 | Comments to Authors | (3) Evaluate OCR text explicitly as an additional modality, since 67.18% of the dataset contains OCR information. Page 4 of 5
R5-04 | Reviewer #5 | Comments to Authors | (4) Add cross-platform evaluation between Threads and Facebook to better quantify domain generalization.
R5-05 | Reviewer #5 | Comments to Authors | (5) Clarify comparisons with ViMMSD, since the datasets use diﬀerent label spaces and evaluation metrics.
R5-06 | Reviewer #5 | Comments to Authors | (6) Expand the error analysis with representative qualitative examples showing where multimodal models fail on the important (0,0,1) cases.
R5-SCORE | Reviewer #5 | Overall Score | Weak Accept

## Grouped requests
Group ID | Grouped concern | Raw feedback IDs | Paper location | Merged request / scope | Primary tasks
G1 | Label semantics and fair comparisons | R3-01; R3-02; R2-08; R4-03 | III.A; III.E; IV.A/E; Table VII | Clarify independent T/I/MM judgments, including M=0 with T=1 or I=1. Audit actual training/evaluation targets before comparing models. | W04; C01; C03; W15
G2 | Annotation reliability and provenance | R2-03; R3-03; R4-01; R4-03; R5-02 | III.D; Tables III–IV; abstract/conclusion | Separate prompt-tuning agreement, LLM–human agreement and independent human–human agreement. Document annotators, corrections, adjudication and test provenance. | W05; W06; W11; C13; W07
G3 | Reproducibility and statistical reliability | R2-05; R3-04; R4-01; R4-03; R5-01 | IV.A–F; Table VII; supplement | Repeat stochastic runs, disclose seeds, estimate uncertainty, and investigate identical ablation scores from inputs through predictions. | C02; C03; C04; C05; C06; W01
G4 | OCR contribution | R2-04; R3-05; R4-02; R5-03 | III.B; IV new OCR subsection; VI | One controlled five-setting experiment: caption-only, OCR-only, caption+OCR, image+caption, image+caption+OCR. Reuse shared caption and image+caption runs. | C08; C09; W02
G5 | Platform bias and generalization | R4-01; R4-03; R5-04 | III.E; IV new platform subsection; limitations | Evaluate Facebook→Threads and Threads→Facebook, with within-platform controls, identical targets and platform/class counts. | C10; W02; W09; W10
G6 | Taxonomy and qualitative diagnostics | R2-04; R5-02; R5-06 | III.C; Table II; V; Figure 4 | Distinguish seven semantic types from modality-label combinations. Analyze type availability and verified examples; expand failures on (0,0,1). | W08; C11; W03
G7 | Novelty, related work and calibrated claims | R2-02; R2-06; R2-08; R4-03; R5-05 | I; II; III.E; IV.E/G; V; VI; abstract | Position the dataset contribution quantitatively. Qualify comparisons across different label spaces and metrics. Replace reliability and superiority overclaims. | W12; W14; W15; W09; W10
G8 | Ethics and release | R2-07; R3-06 | New ethics/data-release subsection; repository | Document actual privacy, anonymization, copyright, platform terms, release license and removal process. Do not claim unverified permission or compliance. | W13; C12

## Rewrite drafts
Draft ID | Writing task | Paper location | Purpose | Proposed rewrite | Verification required before use
D1 | T09 | III.A | Label definitions | T and I represent sarcasm judgments made from the caption and image in isolation, respectively, whereas MM represents the judgment made from the paired post. These judgments are not assumed to follow a logical OR rule: the paired context may change the interpretation of an isolated cue. | Use only after W04 verifies the original guidelines permit context cancellation; add a real positive-unimodal/negative-MM example or revise inconsistent annotations.
D2 | T09 | III.D; Table IV | Agreement interpretation | On the 736 manually verified samples, agreement between the LLM-generated labels and the human-validated labels was κ = 0.7600, 0.7436, and 0.7987 for text, image, and multimodal sarcasm, respectively. These values describe LLM–human agreement; they do not by themselves establish independent human–human reliability or the quality of all training labels. | Original values from paper p.3 Table IV; verify calculation/provenance. Add actual annotator count, blinding, correction rates and independent-audit results after C13/W07.
D3 | T10 | III.E | Interpretation of label counts | Among the 3,223 samples labeled sarcastic at the multimodal level, 1,602 (49.71%) have the label combination (0,0,1). This distribution indicates that joint interpretation is important under the annotation protocol. It does not establish that unimodal predictors are fundamentally inadequate. | Counts from paper p.3 Table VI; reconcile after label audit before use.
D4 | T04 | IV.A–D | Comparable evaluation | For comparisons of input modalities, all models predict the same final MM label using identical train, development, and test sample IDs. Modality-specific T and I prediction is reported separately as a diagnostic task. Model selection uses development data, and the test set is reserved for final evaluation. | Proposed new protocol, not an assertion about completed experiments. Publish only after C01–C03 verifies and implements it; append actual seed and uncertainty methods.
D5 | T08 | New OCR subsection | OCR experiment description | We evaluate five input settings: caption-only, OCR-only, caption+OCR, image+caption, and image+caption+OCR. Comparisons use a shared MM target and matched data splits. We report performance on the full test set and separately on samples with and without OCR text, with the support of each subset. | Proposed methods text only; require C09 completion. Add backbone, preprocessing, missing-OCR behavior, run count and actual estimates.
D6 | T12 | IV.G | Cross-dataset comparison | The original ViMMSD results use a four-class label space and F1-micro, whereas our reimplementations are evaluated on the binary MM target using F1-macro. The absolute scores therefore do not support a direct cross-dataset performance comparison. Differences in architecture rankings are descriptive and may reflect multiple dataset and protocol differences. | Based on current paper p.5 IV.G; W12 must verify the original source and actual reimplementation targets.
D7 | T14 | VI | Calibrated conclusion | ViMMSarc-Fine provides Vietnamese text–image pairs with modality-level sarcasm labels and auxiliary OCR text. Its label distribution supports the value of studying cross-modal interpretation, while the current annotation and evaluation design limits broader conclusions about reliability and model superiority. The revised experiments and audit provide [INSERT VERIFIED FINDINGS], with remaining limitations in [INSERT CONFIRMED LIMITATIONS]. | Draft with explicit placeholders; replace from finalized evidence. Do not retain 68.84% as a comparative headline unless the final shared-target evaluation supports it.
D8 | T13 | New ethics/release subsection | Facts to establish before publication | The dataset was collected from [VERIFIED SOURCE/ACCESS CONDITIONS]. We handle personal information in captions, images, OCR and conversation screenshots by [ACTUAL PROCEDURE]. We distribute [PERMITTED CONTENT] under [VERIFIED LICENSE/TERMS], with [REMOVAL CONTACT/PROCESS]. Content that cannot be shared under the established permissions is [ACTUAL HANDLING]. | A fact-completion template, not a statement of legal compliance; verify each bracket against records and applicable source terms.